CFDMC 2025-2026 Traffic Light Report as of 6-3-26  (see attached Task/Project Report for additional details)

Legend-Blue=Completed; Green=On Target; Yellow =Action Needed; Red=In Jeopardy/Board Action Needed, Orange=High Priority

| Issue/Contract Task / Project / Deliverable | Due | Status |
| --- | --- | --- |
| High Priority Issue: Family Reunification; hospitals need immediate support in managing family/friends (see also FAC project/ FRC exercise) | 6/30/26 | Lead: Drawdy Making progress with Pulsara implementation (plan to have all of Orange County operational by 12/26) Working with Orange County on FRC/FAC plan Presented at FTEM conference in June Pediatric tabletop 3/18/26 focused on reunification Will be working on FRC team plan update |
| High Priority Issue: EMS Engagement (need EMS input and engagement) | TBD | Lead: RTAB Clinical Leadership Committee (Dr. Zuver has lead on scheduling regional call) |
| High Priority Issue: Disaster Patient Movement Process – (need regional process to identify beds for patients – identified as statewide gap during Hurricane Ian) | 6/30/26 | Lead: Dr. Zito and Trauma Clinical Leadership Committee (project plan and SME workgroup identified; will kick off following April exercise State is working with a vendor to do a statewide assessment and project plan |
| High Priority: Engage community leaders (strategic objective) | 12/31/25 | Lead: Board |
| Submit Monthly Expenditures Documentation | Monthly | Submitted each month |
| Task #1 – Royal 4 | Final report due 6/15/26 | Submitted for quarter |
| Task #2 – Data Security & Confidentiality | Quarterly | Submitted for quarter |
| Task #3 – Healthcare Coalition Task Force | Quarterly | Completed |
| Task #4 – Budget | July 15th | Completed |
| Task #5 – Governance | December 15th | Completed |
| Task #6 – HCC Boundaries | December 15th | Completed |
| Task #7 – HVA | December 15th | Completed |
| Task #8 – Readiness Assessment | December 15th | Completed |
| Task #9 – Supply Chain Integrity Assessment | December 15th | Completed |
| Task #10 – Cyber Security Assessment | June 15th | Present to Board for approval on 6/9/26 |
| Task #11 – Extended Downtime Healthcare Delivery Impact Assessment | June 15th | Present to Board for approval on 6/9/26 |
| Task #12 – Provide input into State Strategic Plan | Quarterly | Completed |
| Task #13 – HCC Readiness Plan | December 15th | Completed |
| Task #14 - Training and Exercise Plan | December 15th | Completed |
| Task #15 – HCC Response Plan | June 15th | Present to Board for approval on 6/9/26 |
| Task #16 – HCC COOP | June 15th | Present to Board for approval on 6/9/26 |
| Task #17 – MRSE | June 15th | Present to Board for approval on 6/9/26 |
| Task #18 – Position Descriptions | April 15th | Completed |
| Task #19 – Recovery Plan | June 15th | Present to Board for approval on 6/9/26 |
| Task #20 – Preparedness Workshop | As scheduled | Completed |
| Task #21 – Quarterly Report | Quarterly | Submitted for quarter |

CFDMC Project Report

| Contract Task / Coalition Project | Due Date | Lead / Back-up / Partners | Activities / Status |
| --- | --- | --- | --- |
| Task #1 – Royal 4: Ensure the Royal 4 System is updated throughout the contract term as follows: - Enter all tangible preparedness and response items purchased with contract funds into the Royal 4 system within 30 calendar days of the item invoice date. - Run an Inventory Movement Report to confirm that the Royal 4 System is up to date, ensuring that the start date of the report is the first day in the quarter for which the report is submitted and that the end date of the report is the last day in the quarter for which the report is submitted. - Save the Royal 4 System Inventory Movement Report as a single file and include the task number in the file name at a minimum. - Submit the Royal 4 System Inventory Movement Report file via email to the Contract Manager by October 15, January 15, April 15, and June 15 of each contract year. - Upload the Royal 4 System Inventory Movement Report file in CRVS by October 15, January 15, April 15, and June 15 of each contract year. - Ensure the Royal 4 System Inventory Movement Report is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the Royal 4 System Inventory Management Report is not complete and/or accurate, modify the Royal 4 System Inventory Management Report, and submit and upload the modified Royal 4 System Inventory Management Report in CRVS as directed by the Department. | Quarterly | Meyers (Drawdy, Cook) | Next report due 6/15/26. Most of the equipment will be purchased after that date and will be submitted during the 7/15/26 report. |
| Task #2 – Data Security/Confidentiality Always comply with the terms of the Data Security and Confidentiality provisions (Attachment II) throughout the contract term. | Quarterly | Drawdy (Meyers, Cook) | In compliance |
| Task #3: HCCTF Attend HCCTF meetings and calls as directed by the Department. | Quarterly | Drawdy (Meyers, Cook) | Attended 4/22/26 |
| Task #4 - Budget: Upload the completed HCC Budget using the template at https://floridahealth.sharepoint.com as an Excel file in ASPR’s designated tracking system by July 15. Remove any previous versions of the budget from ASPR’s designated tracking system as applicable. Submit the completed HCC Budget to the Contract Manager via email and in CRVS by July 15. Ensure the HCC Budget is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the HCC Budget is not complete and/or accurate, modify the HCC Budget and submit, and upload the modified HCC Budget as directed by the Department. | 7/15/25 | Drawdy (Meyers, Cook) | Final budget revision to be approved by Board on 6/9/26 FY 26-27 Budget to be approved by Board on 6/9/26 |
| Task #5 – Governance: Maintain, update, and submit HCC governance information throughout the contract term as follows: - Maintain HCC governance information detailing the HCC’s management/ administration, geographic coverage, membership, and community coordination and engagement, following the HCC governance guidance and materials provided by ASPR. - Compile the HCC governance information into a single file and include the task number in the file name at a minimum. Submit the HCC governance information via email to the Contract Manager and upload the file in CRVS and in ASPR’s designated tracking system as applicable by December 15. - Update the HCC governance information as necessary. - Ensure the HCC governance information is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the HCC governance information is not complete and/or accurate, modify the HCC governance information, and submit and upload the modified HCC governance information in CRVS as directed by the Department. | December 15th | Drawdy (Board) | Update approved by Board on 5/19/26 |
| Task #6 - HCC Boundaries: Provide information about the HCCs county boundaries within the HCC Jurisdiction as follows: - Create an HCC Jurisdiction map that includes county boundaries in a single file and include the task number in the file name at a minimum. - Submit the HCC Jurisdiction map in CRVS and ASPR’s designated tracking system by December 15 of each contract year. - Update the jurisdictional information as needed during the contract year to reflect any jurisdictional boundary changes that occur. - Ensure the HCC Jurisdiction map is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the HCC Jurisdiction map is not complete and/or accurate, modify the HCC Jurisdiction map, and submit and upload the modified HCC Jurisdiction map in CRVS as directed by the Department. | December 15th | Drawdy | Completed |
| Task #7 – HVA: Update, distribute, and submit the HVA by December 15 as follows: - Update the HVA detailing the threats and hazards for the jurisdiction, vulnerabilities, probability of occurrence, severity of impact, and priority actions, following the HVA guidance and materials provided by ASPR. - Save the HVA as a single file and include the task number in the file name at a minimum. - Submit the HVA via email to the Contract Manager and upload it in CRVS and ASPR’s designated tracking system by December 15. - Remove previous versions of the HVA from ASPR’s designated tracking system as applicable. - Distribute the HVA to HCC Members by December 15. - Ensure the HVA is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the HVA is not complete and/or accurate, modify the HVA, and submit and upload the modified HVA in CRVS as directed by the Department. | December 15th |  | Completed |
| Task #8 – Readiness Assessment: Update, submit, upload, and distribute a readiness assessment as follows: - Update a readiness assessment detailing the HCC’s capacity and capability to carry out NOFO activities, conduct health care preparedness and response operations, and address health care readiness gaps, using the readiness assessment materials provided by ASPR. - Save the readiness assessment as a single file and include the task number in the file name at a minimum. - Submit the readiness assessment via email to the Contract Manager by December 15. Upload the readiness assessment in CRVS and ASPR’s designated tracking system by December 15. - Upload the readiness assessment in CRVS and ASPR’s designated tracking system by December 15. - Remove any previous versions of the readiness assessment from ASPR’s designated tracking system as applicable. - Distribute the readiness assessment to HCC Members by December 15. - Ensure the readiness assessment is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the readiness assessment is not complete and/or accurate, modify the readiness assessment, and submit and upload the modified readiness assessment in CRVS as directed by the Department. | December 15th | Drawdy (Meyers, Cook) | Completed |
| Task #9 – Supply Chain Integrity Assessment: Update, distribute, upload, and submit the supply chain integrity assessment as follows: - Update the supply chain integrity assessment detailing resource needs, vulnerabilities, current access and infrastructure, impact on communities and mitigation strategies, following the supply chain integrity assessment guidance and materials provided by ASPR. - Save the supply chain integrity assessment as a single file and include the task number in the file name at a minimum. - Submit the supply chain integrity assessment via email to the Contract Manager by December 15. - Upload the supply chain integrity assessment in CRVS and ASPR’s designated tracking system by December 15. - Remove any previous versions of the supply chain integrity assessment from ASPR’s designated tracking system as applicable. - Distribute the supply chain integrity assessment to HCC Members by December 15. - Ensure the supply chain integrity assessment is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the supply chain integrity assessment is not complete and/or accurate, modify the supply chain integrity assessment, and submit and upload the modified supply chain integrity assessment as directed by the Department. | December 15th | Drawdy (Supply Chain Integrity Workgroup) | Completed |
| Task #10 – Cybersecurity Assessment: Update, submit, upload, and distribute the cybersecurity assessment as follows: - Update the cybersecurity assessment detailing cybersecurity practices, community impact, and mitigation strategies, following the cybersecurity assessment guidance and materials provided by ASPR. - Save the cybersecurity assessment as a single file and include the task number in the file name at a minimum. - Submit the cybersecurity assessment email to the Contract Manager by June 15. - Upload the cybersecurity assessment in CRVS and ASPR’s designated tracking system by June 15. - Remove any previous versions of the cybersecurity assessment from ASPR’s designated tracking system as applicable. - Distribute the cybersecurity assessment to HCC Members by June 15. - Ensure the cybersecurity assessment is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the cybersecurity assessment is not complete and/or accurate, modify the cybersecurity assessment, and submit and upload the modified cybersecurity assessment in CRVS as directed by the Department. | June 15th | Drawdy | Update to be approved by Board on 6/9/26 |
| Task #11 – Extended Downtime Healthcare Delivery Impact Assessment: Update, distribute, upload, and submit the extended downtime health care delivery impact assessment as follows: - Update the extended downtime health care delivery impact assessment detailing impacted functions, community impact, and mitigation strategies, the extended downtime health care delivery impact assessment guidance and materials provided by ASPR. - Save the extended downtime health care delivery impact assessment as a single file and include the task number in the file name at a minimum. - Submit the extended downtime health care delivery impact assessment via email to the Contract Manager by June 15. - Upload the extended downtime health care delivery impact assessment in CRVS and ASPR’s designated tracking system by June 15. - Remove any previous versions of the extended downtime health care delivery impact assessment from ASPR’s designated tracking system as applicable. - Distribute the extended downtime health care delivery impact assessment to HCC Members by June 15. - Ensure the extended downtime health care delivery impact assessment is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the extended downtime health care delivery impact assessment is not complete and/or accurate, modify the extended downtime health care delivery impact assessment, and submit and upload the modified extended downtime health care delivery impact assessment as directed by the Department. | June 15 | Drawdy | Update to be approved by Board on 6/9/26 |
| Task #12 – State Strategic Plan: Provide input into the state-level strategic plan as follows: - Participate in the annual Preparedness Advisory Committee (PAC) meeting and other activities as directed by the Department. | Quarterly | Drawdy | Completed Attended Statewide Preparedness Advisory Council meeting 3/23/26 |
| Task #13 – HCC Readiness Plan: Update, submit, upload, and distribute an HCC Readiness Plan as follows: - Update the HCC Readiness Plan to provide a roadmap for the HCC to address strategic priorities, implement the cooperative agreement activities, and develop and grow as an organization by December 15, following the readiness plan guidance and materials provided by ASPR. - Save the HCC Readiness Plan as a single file and include the task number in the file name at a minimum. - Submit the HCC Readiness Plan via email to the Contract Manager by December 15. - Upload the HCC Readiness Plan in CRVS and ASPR’s designated tracking system by December 15. - Remove any previous versions of the HCC Readiness Plan from ASPR’s designated tracking system as applicable. - Distribute the HCC Readiness Plan to HCC Members by December 15. - Ensure the HCC Readiness Plan is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the HCC Readiness Plan is not complete and/or accurate, modify the HCC Readiness Plan, and submit and upload the modified HCC Readiness Plan in CRVS as directed by the Department. | December 15th | Drawdy (Meyers, Cook) | Completed |
| Task #14 - Training and Exercise Plan: Update, submit, upload, and distribute a training and exercise plan as follows: - Update the training and exercise plan of projected trainings and exercises through June 30, 2029, using the training and exercise materials provided by ASPR. - Save the training and exercise plan as a single file and include the task number in the file name at a minimum. - Submit the training and exercise plan via email to the Contract Manager by December 15. - Upload the training and exercise plan in CRVS and ASPR’s designated tracking system by December 15. - Remove any previous versions of the training and exercise plan from ASPR’s designated tracking system as applicable. - Distribute the training and exercise plan to HCC Members by December 15. - Ensure the training and exercise plan is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the training and exercise plan is not complete and/or accurate, modify the training and exercise plan, and submit and upload the modified training and exercise plan in CRVS as directed by the Department. | December 15th | Drawdy (Meyers, Cook) | Completed |
| Task #15 - HCC Response Plan: Update, submit, upload, and distribute an HCC Response Plan as follows: - Update the HCC Response Plan to detail how the HCC will implement activities that support the Core Functions in the NOFO, following the response plan guidance and materials provided by ASPR. - Save the HCC Response Plan as a single file and include the task number in the file name at a minimum. - Submit the HCC Response Plan via email to the Contract Manager by June 15. - Upload the file in CRVS and ASPR’s designated tracking system by June 15. - Remove previous versions of the HCC Response Plan from ASPR’s designated tracking system as applicable. - Distribute the HCC Response Plan to HCC Members by June 15. - Ensure the HCC Response Plan is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the HCC Response Plan is not complete and/or accurate, modify the HCC Response Plan, and submit and upload the modified HCC Response Plan in CRVS as directed by the Department. | June 15 | Drawdy (Meyers, Cook) | Update to be approved by Board on 6/9/26 |
| Task #16 – COOP: Update, submit, upload, and distribute a COOP as follows: - Update a COOP that is informed by the HCC Members’ COOP, following the COOP guidance and materials provided by ASPR. - Save the COOP as a single file and include the task number in the file name at a minimum. - Submit the COOP file via email to the Contract Manager by June 15. - Upload the COOP file in CRVS and ASPR’s designated tracking system by June 15. - Remove previous versions of the COOP from ASPR’s designated tracking system as applicable. - Distribute the COOP to HCC Members by June 15. - Ensure the COOP is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the COOP is not complete and/or accurate, modify the COOP, and submit and upload the modified COOP as directed by the Department. | June 15th | Meyers (Drawdy, Cook) | Update to be approved by Board on 6/9/26 |
| Task #17 – MRSE: Hold a MRSE by May 31, to assess the HCC's capacity to support a large-scale, community-wide medical surge incident, following the MRSE materials provided by ASPR. Upload and submit documentation of a MRSE as follows: - Invite the BPR Training and Exercise Section Administrator via email to participate in the MRSE, a minimum of 30 calendar days prior to the exercise. - Save the completed ASPR MRSE documentation as a single file and include the task number in the file name at a minimum. - Submit the completed ASPR MRSE Exercise Planning and Evaluation Tool via email to the Contract Manager and upload it in CRVS and ASPR’s designated tracking system within 90 calendar days following the exercise or no later than June 15, whichever occurs first. - Ensure the ASPR MRSE Exercise Planning and Evaluation Tool is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the ASPR MRSE Exercise Planning and Evaluation Tool is not complete and/or accurate, modify the ASPR MRSE Exercise Planning and Evaluation Tool, and submit and upload the modified ASPR MRSE Exercise Planning and Evaluation Tool in CRVS as directed by the Department. | June 15th | Drawdy & FSE Planning Team | AAR-IP to be approved by Board on 6/9/26 Enter MRSE data by 6/15/26 and upload AAR-IP |
| Task #18 – Position Descriptions . Update, upload, and submit job descriptions as follows: - For each individual who receives HPP funds as part or all of their salary/benefits, complete a job description. - Save the job description(s) as a single file and include the task number in the file name at a minimum. - Submit the job description(s) file via email to the Contract Manager by April 15. - Upload the job description(s) file in CRVS by April 15. - Ensure the job descriptions file is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the job descriptions file is not complete and/or accurate, modify the job descriptions file, and submit and upload the modified job descriptions file in CRVS as directed by the Department. | April 15th | Drawdy | Completed New position to be added in FY 26-27 |
| 19: Recovery Plan Develop, distribute, and submit a recovery plan as follows: - Develop a recovery plan describing how the HCC will integrate with key partners, support the workforce, recover critical infrastructure, and manage community impact, following the recovery plan guidance and materials provided by ASPR. - Save the recovery plan as a single file and include the task number in the file name at a minimum. - Submit the recovery plan via email to the Contract Manager by June 15. - Upload the recovery plan in CRVS and ASPR’s designated tracking system by June 15. - Remove any previous versions of the recovery plan from ASPR’s designated tracking system as applicable. - Distribute the recovery plan to HCC Members by June 15. - Ensure the recovery plan is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the recovery plan is not complete and/or accurate, modify the recovery plan, and submit and upload the modified recovery plan in CRVS as directed by the Department. | June 15th | Drawdy | Will be included in Response Plan. Update to be approved by Board on 6/9/26 |
| 20. Preparedness Workshop:` Participate in the 2026 preparedness workshop as follows: - Participate in person in the 2026 preparedness workshop as directed by the Department. | Upon demand | Drawdy | Completed |
| 21. Quarterly Report Complete, upload, and submit the Quarterly Progress Report as follows: - Document the date of each update to the Royal 4 Systems in the corresponding Quarterly Progress Report. - Document compliance the Data Security and Confidentiality provisions (Attachment II) by providing a statement or attestation certifying this requirement is met in each Quarterly Progress Report. - Document the date of each HCCTF meeting or call and the name of each of Provider’s staff in attendance in the corresponding Quarterly Progress Report. - Document a summary of any updates to the HCC Budget in the corresponding Quarterly Progress Report. - Document any updates to the governance information in the corresponding Quarterly Progress Report. - Document any HCC jurisdictional changes in the corresponding Quarterly Progress Report. - Document the date and method the HVA was distributed to HCC members in the corresponding Quarterly Progress Report. - Document the date and method the readiness assessment was distributed to HCC Members in the corresponding Quarterly Progress Report. - Document the date and method the supply chain integrity assessment was distributed to HCC Members in the corresponding Quarterly Progress Report. - Document the date and method the cybersecurity assessment was distributed to HCC Members in the corresponding Quarterly Progress Report. - Document the date and method the extended downtime health care delivery impact assessment was distributed in the corresponding Quarterly Progress Report. - Document the date of each PAC meeting or activity and the name of each of Provider’s staff who participated in the corresponding Quarterly Progress Report. - Document the date and method the HCC Readiness Plan was distributed to HCC Members in the corresponding Quarterly Progress Report. - Document the date and method the training and exercise plan was distributed to HCC Members in the corresponding Quarterly Progress Report. - Document the date and method the HCC Response Plan was distributed to HCC members in the corresponding Quarterly Progress Report. Document the date and method the COOP was distributed to HCC Members in the corresponding Quarterly Progress Report. - Document the date, if known, of the planned or completed MRSE in each quarter’s Quarterly Progress Report. - Document the date of the email invitation to the BPR Training and Exercise Section Administrator to participate in the MRSE in the corresponding Quarterly Progress Report. - Document the name of the BPR representative who participated in the MRSE in the corresponding Quarterly Progress Report. - Document any HCC job description changes in the corresponding Quarterly Progress Report. - Document the date and method the recovery plan was distributed to HCC members in the corresponding Quarterly Progress Report. - Document the date(s) of the workshop and the name of each of Provider’s staff who participated in the corresponding Quarterly Progress Report. - Include the progress for each Task in the Quarterly Progress Report. - Save the Quarterly Progress Report as a single file and include the task number in the file name at a minimum. - Submit the Quarterly Progress Report within 15 calendar days after the end of each quarter via email to the Contract Manager and upload it in CRVS. - Ensure the Quarterly Progress Report is complete and accurate at the time of submission and when uploaded in CRVS. In the event the Department determines the Quarterly Progress Report is not complete and/or accurate, modify the Quarterly Progress Report, and submit and upload the modified Quarterly Progress Report in CRVS as directed by the Department. | Quarterly | Drawdy | Final report due 7/15/26 |
| Coalition Project: Update Preparedness & Response annexes that are not contract tasks | Ongoing | Drawdy (Meyers, Cook, Workgroups, Board) | Updates to be approved by Board on 6/9/26 |
| Coalition Project – Quarterly Community Based Drills - September – Operation Protect & Secure (active shooter) - December – A Glass of Mutual Aids (mutual aid confirmations) - February – Great Tornado Drill (shelter in place) - May – Operation Generate Confidence (generator drill) | Quarterly | Drawdy / Cook county Ems | Completed Great Tornado Drill 2/5/26. Completed generator drill is May 27th Moved Mutual Aid drill to June Planning extended downtime drill at December conference |
| Coalition Project – other exercises |  | Drawdy (EID Collaborative) | Pediatric Pandemic TTX March 28. AAR-IP to be approved by Board 6/9/26 Participating in NDMS FCC Exercise May 13th (sent Ocoee ambu-bus, several evaluators, Orlando VA playing) |
| AAR/IP - FSED BEST PRACTICE GUIDE - TRAUMA/BURN TRAINING |  |  | COMPLETED - Completed trauma/burn training – sent out statewide and submitted/accepted at national conference - Updated FSED best practice guide with FSED MCI card list, trauma/burn training link and ASPR |
| Monthly Expenses: Provide documentation for all payments made by Provider as a direct result of services provided or goods purchased through the funding of this contract and submit to Contract Manager and HCC Florida HCC SharePoint within 15 business days following the end of each month. Such documentation includes timesheets, canceled checks (if available), bank statements, receipts, invoices paid, or other documentation that supports proof of payment. | 15 business days following the quarter | Drawdy | Submitted monthly |
| Single federal audit: organizations receiving more than $750,000 annually are required to undergo a single federal audit by 9/30 annually. | 6/30/26 | Drawdy | Beginning 2025 single federal audit in June |
| IRS 990 | November 30 annually | Drawdy | To be completed by auditor following audit |
| Coalition Project: Communicate with members - Sent out alerts, training and exercise opportunities (Drawdy) - Keep website updated (Meyers) - Quarterly member meetings (all) - Quarterly communication drills (Drawdy & Cook) | Quarterly | Drawdy | Need to identify non-power communications drill Quarterly comms drill during April exercise |
| Coalition Project: EMResource EMResource Steering Committee is establishing best practice guidelines and training videos Ranked high as UASI project (expect to receive funding to sustain) | Quarterly | Meyers (Drawdy, Cook, Hospitals, EM, EMS, FHA) | UASI funding through May 2027 Working to identify which counties are not using EMResource and develop engagement plan |
| Coalition Project: Hospital Minimum Readiness Maintain hospitals at minimum readiness standards (by hospital size Monthly hospital calls | June 30 Annually | Drawdy (Meyers, Cook, Hospitals, Board) | Ongoing We expect to meet all needs this fiscal year Will publish 26-27 list by May 19th |
| Coalition Project: FAC Team | Annual | Drawdy (Meyers, Cook, Team Members, Board) | Will work to revise/simplify plan and recruit new team members |
| Coalition Project: Regional Trauma Advisory Board (Executive Committee, Clinical Leadership Committee, Preparedness Committee (RTCC plan), System Support Committee | Annual | Drawdy (Meyers, Cook, RTAB Members) | Committees meeting bimonthly Executive Committee: focus on whole blood in field Launched new Extended Care Committee System Support will lead statewide STB project Clinical Leadership Committee will lead patient movement/RMOCC planning |