2025 Regional Mass Casualty Exercise

Initial Planning Meeting Agenda

January 9, 2026 at 9:00 AM

Zoom link:

https://us06web.zoom.us/j/3615841429?pwd=ZGExVXdSVmdXVnAzY2J4dy91UXI5UT09

Meeting ID: 361 584 1429, Passcode: q8C2Cf

Exercise Purpose:   The purpose of the exercise is to demonstrate during a mass casualty event hospitals’ capability to meet the ASPR HPP medical surge capability, demonstrate the ability of the region’s response systems to meet the needs of the community in a mass casualty, and demonstrate the ability of the Coalition to provide resource coordination and situational awareness to members.

Exercise Scope/Date/Time/Location (confirmed):    This will be a full scale exercise at hospitals and other locations across Regions 4 and 5,  on Thursday, April 9, 2026 from 8 am to noon.

Review Draft and Finalize Exercise Scenario:   See attached draft

Review/Finalize Exercise Capabilities & Objectives:  Planning Team Discussion

| Objective | Capability |
| --- | --- |
| Objective 1: Evaluate the hospitals’ ability to demonstrate Hospital Incident Command System (HICS) in response to a major incident. | ASPR HPP Capability #2: Healthcare and Medical Response Coordination |
| Objective 2: Assess hospital facilities’ ability to activate and implement infrastructure protection measures in response to a major incident in accordance with policies and procedures. | ASPR HPP Capability #3: Continuity of Healthcare Service Delivery |
| Objective 3: Evaluate hospital facilities’ ability to activate and execute decontamination, triage, medical surge, and resource management in response to a major incident in accordance with policies and procedures. | ASPR HPP Capability #4: Medical Surge NOTE: Hospitals must report on MRSE Performance Measures |
| Objective 4: Assess community partners’ ability to share and receive timely communications to support security and assist with situational awareness and operational decisions during an incident in the community, utilizing the communications platforms available within the region. Review & Update: Last year we said we wanted to ensure communication and operational coordination across disciplines, across counties, and now across Regions 4 & 5. | ASPR HPP Capability #2: Healthcare and Medical Response Coordination |
| Objective 5: Activate the county emergency operations centers (EOCs) in response to a weapon of mass destruction (WMD) incident at mass gathering events and effectively demonstrate coordination and communication with healthcare and critical infrastructure partners. | ASPR HPP Capability #2: Healthcare and Medical Response Coordination |
| Objective 6: Test acute care hospital and free-standing emergency departments’ capability to stabilize and/or treat high number of burn patients. | ASPR HPP Capability #4: Medical Surge |
| Objective 7: Escalating Incident: Ability for healthcare organizations to identify that an incident or incidents are escalating and will need additional support from within their systems beyond normal emergency response practices to ensure continuity of operations for patients. This may involve response from the organization’s most senior leadership and board members. | ASPR HPP Capability 3. Continuity of Health Care System Delivery ASPR HPP Capability 4. Medical Surge |
| Objective 8: Cyber Incident: Ensure healthcare organizations can continue to operate when faced with a cyberattack that poses significant effects on patient care and/or organizational continuity. | ASPR HPP Capability 3. Continuity of Health Care Service Delivery; Objective 4: Develop Strategies to Protect Health Care Information Systems and Networks (Page 37). |
| Objective 9: Demonstrate the ability of response staff at participating facilities and agencies (i.e., EMS, Hospitals) to receive notification of a nerve agent / organophosphate and initiate procedures consistent with the request and activation of a CHEMPACK, in accordance with local procedures and access restrictions as set forth by the Center for the Strategic National Stockpile. Will be reviewed and updated based on scenario | ASPR HPP Capability 4. Medical Surge |
| Objective 10: Test Free Standing Emergency Department (FSED) Best Practice Guidelines with FSEDs participating in the exercise. Remove – this was tested in 2025. | ASPR HPP Capability 4. Medical Surge |
| Objective 11: Test family reunification processes Discuss – how will this be tested? | ASPR HPP Capability 4. Medical Surge |

Players:

- Hospitals/FSEDs (see attached list)

- Emergency Management – Orange and Osceola/Functional, Seminole/Full Scale.  Reaching out to other county emergency managers to determine their level of play

- EMS (we need to identify full scale play by at least one agency)

Exercise Action Plan:

| Action | Lead | Due Date | Status |
| --- | --- | --- | --- |
| Prepare for, facilitate and document planning meetings | Coalition / Danielle Balser | Ongoing | C&O Completed 12/5/25 |
| Gather and report Player Information (hospitals, EMS, EM, etc.) | Coalition | 1/7/26 | Spreadsheet sent to hospitals |
| Gather and report hospital needs (re victims, logistics, EMS, LE, etc. | Coalition | 2/28/26 |  |
| Coordinate Emergency Management involvement | Harris / Balser |  | Seminole Full Scale Orange Full Scale Osceola Functional Note: encourage all EMs to participate. Would like to track ESF8 requests/response this year |
| Finalize scenario | FBI drafted; planning team to approve | 1/8/26 |  |
| Solicit exercise names | Coalition | 1/15/26 |  |
| Vote to select exercise name | Planning Team | 1/31/26 |  |
| Draft exercise logo | Boone HS Graphics | 2/15/26 |  |
| Vote to select exercise logo | Planning Team | 2/28/26 |  |
| Draft Exercise Plan | Coalition / Balser | 3/15/26 |  |
| Communications Plan | Coalition | 3/31/26 |  |
| Coordinate EMS support (ambulances for hospitals) | Amanda Freeman & Coalition | 3/31/28 |  |
| Notify & engage RDSTF partners | Steve Brenton | 3/31/26 |  |
| Coordinate local law enforcement involvement support | Steven Brenton | 3/31/26 |  |
| Coordinate FBI Involvement (bad guy actors, etc.) | Tim Callinan | 3/31/26 |  |
| Integrate Disaster Behavioral Health for Victims/Responders | Lynda W. G. Mason & Maria Bledsoe | 3/31/26 |  |
| Develop MSEL | MSEL Workgroup | 3/31/26 |  |
| Identify and train MRSE Data Collectors | Coalition & Hospitals | 4/5/26 |  |
| Volunteer Management: - Match schools to hospitals - Flyers to register victim volunteers - Identify volunteer reception center and/or hospital staging areas - Waiver (English & Spanish) - Instructions (hospitals, teachers, victims, etc.) - T-shirts - Moulage | Coalition | 3/31/26 |  |
| Develop triage tags | TBD | 3/31/26 |  |
| Develop transportation plan | Coalition with Lynx, public schools, etc. | 3/31/26 |  |
| Recruit, Assign, Train Evaluators / Controllers | Coalition | 3/31/26 |  |
| Recruit, Assign, Train Volunteer Management Staff | Coalition | 3/31/26 |  |
| PIOs | TBD | 3/31/26 | Identify exercise PIO Identify player media contacts |
| Press release | Coalition/Planning Team | 4/1/26 |  |
| Exercise Follow-ups - Gather data - Hold AAR/ Capabilities meeting, Exercise Debrief - Draft AAR - Report MRSE data | Coalition | 5/31/26 |  |

Open Discussion: Local Issues/Concerns/Sensitivities:  Planning Team Discussion

Future Meeting Dates:

- Mid-Term Planning Meeting:  Friday, February 6th at 9 am

- Final Planning Meeting:  Friday, March 6th at 9 am

- Final Check:  Friday, April 3rd at 9 am

- Exercise:   April 9, 2026 – 8 am to noon

- Rain Date:   April 10, 2026

- MRSE Training:  Monday, April 6th at 1 pm

- Evaluator Training:  Monday, April 6th at 2 pm

- Volunteer Management Training: Monday, April 6th at 3:30 pm

- After Action Meeting/Capabilities:  Friday, May 8th at 9 am

- Exercise Planning/Execution Debrief:  Friday, May 8th at 10 am